## Slide 1: Gulf of Guinea Northern Regions Social Cohesion (SOCO) Project
MONITORING AND EVALUATION

## Slide 2: The need to conduct M&E on SOCO Project
Monitoring will allow project stakeholders to track how project activities/interventions are being implemented towards achievement of outputs and some specific objectives/outcomes
This is a continuous activity undertaken regularly to ensure that the right things are being done at the right time.
It measures progress towards implementation of work-plan/action plan
Monitoring helps to identify implementation challenges and mitigation measures/solution offered to improve implementation.

## Slide 3: The need to conduct M&E on SOCO Project
Data from Monitoring provides evidence for managerial decision making
Monitoring ensures accountability by providing donors and stakeholders with the results of project implementation
Monitoring is done internally by project staff using monitoring tools/templates
Monitoring template captures all output indicators and some immediate outcome indicators

## Slide 4: The need to conduct M&E on SOCO Project
EVALUATION is a periodic assessment of changes (Positive and Negative) in the lives of target population attributable to the project.
It assesses the extent to which project overall objectives and outcomes are being achieved (Effectiveness)
It provides lessons for improving project design , programming and implementation
It assesses the extent to which the project is being efficient with the use of resources , whether the benefits will last (sustainability), and the difference being made by the intervention(Impact)
A baseline survey will be undertaken to form the basis for tracking future changes brought about by the project.

## Slide 5: The need to conduct M&E on SOCO Project
A Mid-Term Review (MTR) will be conducted to assess the progress being made towards meeting the PDO and intermediate levels outcomes and propose any modifications thereof
Two beneficiary surveys will be conducted throughout the project’s lifetime to inform survey-based indicators (mostly on beneficiaries' perceptions).
1st survey in Year 2 to inform Mid-Term Result (MTR) and 2nd survey in Year 5 (final year).

## Slide 6: PARTICIPATORY MONITORING AND EVALUATION
PM&E is about strengthening primary stakeholders’ involvement as active participants in interventions by them taking the lead in tracking and analysing progress towards jointly agreed results and deciding on corrective action.
This approach contributes to demand-led planning and decision-making and improved accountability.
Local stakeholders determine what should be measured and how and when monitoring and evaluation should be done.
It empowers community members, improves commitment , ownership and sustainability

## Slide 7: MONITORING AND EVALUATION RESPONSIBILiTIES ACROSS LEVELS
LEVEL | ROLE
Regional Level | The RPCU under the RCC, with support from the Zonal Coordinators, will collate and harmonise the project’s work plan and budget from participating Districts within the region and undertake quarterly monitoring of project implementation in districts within their jurisdiction.
District Level | The DA shall be responsible for the overall project implementation at the local level. The Planning Unit shall review and incorporate project activities into the DMTDP and DA’s AAP. The Budget Unit will incorporate Project budgets into the Composite Budget and the Annual Budget estimate of the Assembly

## Slide 8: MONITORING AND EVALUATION RESPONSILBILTIES ACROSS LEVELS
LEVEL | ROLE
District Level | The DPCU , in collaboration with the Zonal Office and the PIU, ensures appropriate sub-project design, implementation , monitoring and supervision Districts will undertake monthly and quarterly monitoring using a monitoring template which covers the results framework indicators . DAs will also monitor activities at the community level reported by the CFs and CPICs. DA Officers will be given a monitoring template with indicators to look out for when they go to the field to undertake monitoring.
Community Level | CFs assigned to a particular community/cluster are responsible for collecting basic data under the Comprehensive Results Framework to feed the Project M&E system CFs and CPICs will undertake regular monitoring of subproject progress. The CPICs will report all cases of complaints and harassment to the Assembly through the Community Facilitator (CFs).
Notes: Critical to the success of interventions

## Slide 9: WHAT WILL BE MONITORED BY COMMUNITY ACTORS
Planned activities in the community action plan Expected start date and actual start date Expected end date and actual end date Expected and actual number of persons to be employed Expected cost and actual cost of the project Level of community participation on the project Materials being supplied to the site and how the materials are being used Flow of resources for carrying out the project Adherence to environmental and social requirements Adherence to technical specification of the project Pace of Progress of work | 
Notes: Critical to the success of interventions

## Slide 10: MONITORING PROCEDURES
Field monitoring report formats would be developed and used by all field officers at the ZCOs, RCCs and DAs to ensure harmony in reporting relevant information, effecting corrective action and providing feedback.
DAs and ZCOs will be provided with the necessary support in the form of required logistics and training to make short video documentation with commentary at the start of every intervention or stage of activity to give a baseline impression.
Video documentation would be done for a sample of communities for each type of intervention and for peculiar/extra-ordinary situations that can form the basis of case studies.

## Slide 11: REPORTING
During implementation, reports will emanate from the community level through the CFs. The two sets of facilitators will report to the district, regional and zonal to the national level.
At the Community level, the CFs shall be responsible for reporting and to ensure standardisation and uniformity of reports emanating from the various intervention communities, the latter will be provided with simple templates with which they will be required to compile monthly data and submit same to the DA for analysis and collation into a monthly report.
At the DA level, the Focal persons for the departments implementing activities in sub-components areas under components 1 and 2 working through the DPCU (with the DCD as head) shall be responsible for reporting.

## Slide 12: REPORTING
The ZCO shall collate inputs from the various Implementing DAs on the components into a quarterly progress report and submit the same to the PIU as a part of the entire Zonal Report within 20 days after the end of the quarter using the Project MIS system.
From the Quarterly Reports received from the zones, the M&E Specialist shall compile national quarterly reports on the technical and financial aspects of the project and submit them to the MLGDRD through the Project Coordinator.
Quarterly progress reports shall be submitted to the World Bank through the Chief Director of MLGDRD at most 30 days after the end of the quarter.

## Slide 13: THANK YOU!